## Task List
Title | Type | Status | Priority | Assignee | StartDate | DueDate | Description | ParentTitle
Sprint 1 — Backend Foundation | Epic | Doing | High | Andi Pratama | 2024-05-01 | 2024-05-31 | All backend tasks for sprint 1
Setup PostgreSQL Database | Task | Done | High | Erik Setiawan | 2024-05-01 | 2024-05-03 | Install, configure, and seed initial schema
Create users table migration | Subtask | Done | High | Erik Setiawan | 2024-05-01 | 2024-05-02 | users, sessions, roles tables | Setup PostgreSQL Database
Create projects table migration | Subtask | Done | Medium | Erik Setiawan | 2024-05-02 | 2024-05-03 | projects + related foreign keys | Setup PostgreSQL Database
REST API — Authentication | Task | Doing | Critical | Erik Setiawan | 2024-05-04 | 2024-05-10 | Login, logout, token validation endpoints
Login endpoint POST /auth/login | Subtask | Done | Critical | Erik Setiawan | 2024-05-04 | 2024-05-06 | bcrypt verify + session token creation | REST API — Authentication
Logout endpoint POST /auth/logout | Subtask | Doing | High | Erik Setiawan | 2024-05-07 | 2024-05-08 | Invalidate session token | REST API — Authentication
Unit tests for auth endpoints | Subtask | Backlog | Medium | Budi Santoso | 2024-05-09 | 2024-05-10 | 90%+ test coverage required | REST API — Authentication
REST API — Projects CRUD | Task | Backlog | High | Erik Setiawan | 2024-05-11 | 2024-05-17 | GET/POST/PUT/DELETE /api/projects
REST API — Tasks CRUD | Task | Backlog | High | Erik Setiawan | 2024-05-18 | 2024-05-24 | GET/POST/PUT/DELETE /api/tasks
Sprint 1 — Frontend | Epic | Doing | High | Budi Santoso | 2024-05-01 | 2024-05-31 | All frontend tasks for sprint 1
Dashboard page layout | Task | Done | High | Budi Santoso | 2024-05-01 | 2024-05-05 | KPI cards, charts, deadline list
Kanban board component | Task | Doing | High | Budi Santoso | 2024-05-06 | 2024-05-14 | Drag & drop task cards per status column
Drag and drop implementation | Subtask | Doing | High | Budi Santoso | 2024-05-10 | 2024-05-12 | Mouse event drag, optimistic update to API | Kanban board component
Task card design | Subtask | Done | Medium | Budi Santoso | 2024-05-06 | 2024-05-08 | Priority badge, assignee, dates display | Kanban board component
Project modal form | Task | Backlog | Medium | Citra Dewi | 2024-05-15 | 2024-05-20 | New/edit project with file upload support
Gantt chart page | Task | Backlog | Low | Budi Santoso | 2024-05-21 | 2024-05-28 | Horizontal bar chart grouped by project
Write API integration docs | Task | Backlog | Low | Citra Dewi | 2024-05-25 | 2024-05-31 | Postman collection + README update
QA — Sprint 1 regression test | Task | Backlog | High | Deni Kurniawan | 2024-05-29 | 2024-05-31 | Full regression on all sprint 1 features
Deploy to staging server | Task | Backlog | Critical | Erik Setiawan | 2024-05-30 | 2024-05-31 | Docker compose + env setup on staging

## Instructions
PM DASHBOARD — Import Guide
COLUMN REFERENCE
Title ★ | Required. Name of your task, epic, or subtask. | e.g. Setup Database
Type | Task (default), Epic, or Subtask. | Epic / Task / Subtask
Status | Backlog (default), Doing, Review, or Done. | Backlog / Doing / Review / Done
Priority | Low, Medium (default), High, or Critical. | Low / Medium / High / Critical
Assignee | Full name — must exactly match the name in the system. | e.g. Erik Setiawan
StartDate | Start date in YYYY-MM-DD format. | 2024-05-01
DueDate | Due date in YYYY-MM-DD format. | 2024-05-31
Description | Optional task notes or details. | Free text
ParentTitle | For Subtask only. Must exactly match the parent task Title. | e.g. Setup Database
RULES
1. Title is required | Every row must have a Title — blank rows are skipped.
2. Epics are saved first | Create Epics before referencing them as parents.
3. ParentTitle matching | Must be exact match (case-insensitive) to a Title in file.
4. Date format | Always use YYYY-MM-DD (ISO 8601). Other formats may fail.
5. Dropdown validation | Columns B, C, D have dropdown lists — use those values only.
6. Do not add columns | Extra columns are ignored but may cause confusion.
7. Sheet name | The importer reads the first sheet regardless of name.
TIPS
Bulk upload limit | No hard limit, but 500 tasks per upload is recommended.
Subtask ordering | Place Epic rows above their Subtask rows in the file.
Template download | Use the Download Template CSV button in the app for CSV.